## Outline
Projects | 2019 Timeline
| 2019-01-01 |  |  |  | 2019-02-01 |  |  |  | 2019-03-01 |  |  |  | 2019-04-01 |  |  |  | 2019-05-01 |  |  |  | 2019-06-01 |  |  |  | 2019-07-01 |  |  |  | 2019-08-01 |  |  |  | 2019-09-01 |  |  |  | 2019-10-01 |  |  |  | 2019-11-01 |  |  |  | 2019-12-01
| W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
1.0 Lived Experience Advisory Group
1.1 Terms of Reference | bar: 2019-01-01 W1 to 2019-01-01 W4
1.11 ratification by group
1.12 finalize membership of group
1.2 Engage Decision Makers
1.21 define list of new decision makers to engage
1.22 determine asks for invitation letter and meeting with decision makers
1.23 draft and send letters of invitation to decision makers
1.24 meet with decision makers for policy change and advocacy
1.25 determine next steps with decision makers to implement changes
1.3 Education/ Training | bar: 2019-02-01 W2; 2019-04-01 W2; 2019-06-01 W2; 2019-08-01 W2; 2019-10-01 W2
1.31 determine timeline for training
1.32 determine training opportunities
1.33 collaborate with partners to desgin and implement training
1.4 Growth of LEAG | bar: 2019-01-01 W1 to 2019-03-01 W4
1.41 determine stronger framework for sustainable successes
1.42 collaborate with group on new framework
1.43 implement new framework
1.5 Determine 2020 Projects | bar: 2019-11-01 W1 to 2019-12-01 W4
1.51 deliberate progress and new directions
2.0 Community Plan
2.1 Working Group
2.11 determine 3-4 people to sit on working group
2.12 contact and prep group members to join
2.13 send letters of participation (incl. total time per month, time outside meetings, assoc. tasks)
2.14 confirm participation, schedule meetings
2.15 draft community engagement strategy
2.2 Top 100 Exercise | bar: 2019-01-01 W1 to 2019-01-01 W4
2.21 send sector-ranked top 100 list to CLC
2.22 rank people in each sector w/ CLC
2.23 determine 1-2 people per sector as representatives to invite other top 100
2.24 determine which member of CLC to contact representatives
2.25 support CLC memebers contact and gain commitment of representatives
2.3 Letter of Invitation | bar: 2019-01-01 W1 to 2019-02-01 W3
2.31 review example letter from Iowa
2.32 determine areas needing change
2.33 retrieve community-based stats to add to letter
2.34 personalize letters for each sector with name of sector representative
2.35 review letter with working group and CLC
2.36 support CLC members sending letter through representatives (2 month before BG)
2.4 Presentations | bar: 2019-01-01 W1 to 2019-04-01 W2
2.41 review 3 types of presentations
2.42 seek example presentations from Iowa for layout, design, and information required
2.43 retrieve required stats with working group
2.44 design presentations for Big Gathering
2.45 review presentations with Paul
2.46 review presentations with working group
2.5 Agenda | bar: 2019-03-01 W2 to 2019-04-01 W2
2.5 review example agenda from Iowa
2.51 determine agenda layout and flow
2.52 create draft agenda based on Iowa's layout
2.53 review agenda with Paul and working group
2.6 Big Gathering Logistics | bar: 2019-01-01 W1 to 2019-05-01 W3
2.61 determine date and location of Big Gathering
2.62 determine location of Big Gathering
2.63 gather and train recording team
2.64 organize food, seating, and other logistics for the Big Gathering
2.65 Update website to host event page
2.66 Confirm attendance of top 100 partners
2.67 confirm attendees have correct information on Big Gathering
2.68 identify and confirm a facilitator for the event - Paul?
2.69 attend other events in CK to build momentum up to the Big Gathering
2.610 identify and confirm speakers for various parts (representatives?)
2.611 create marketing materials (eg. Sticky note wall, signs, badges, pamphlets, etc.)
2.612 develop ask (willingness to receive more communication, co-host consultations, sit on CLC, etc. )
2.7 Support CLC
2.71 work closely with CLC Co-Chairs to confirm understanding of new directions
2.72 engage CLC in activities related to the Big Gathering and Commmunity Plan
2.73 confirm all CLC attendance at Big Gathering
2.8 Listening Teams | bar: 2019-04-01 W2 to 2019-12-01 W4
2.81 seek volunteers for the listening teams
2.82 establish listening team
2.83 establish schedule (dates and locations) of community meetings, focus groups, interviews
2.84 schedule listening team to gather input and data (cross-over with Poverty Revealed)
2.85 reach out to partners to co-host engagement events
2.86 develop key questions, record answers from engagement (w/ listening team + Sarah)
2.87 develop communications to update people on what is being heard (website page?)
2.88 write a listening report
2.89 review listening report with engaged community
2.9 Quick-win Action Teams (6-8 mnts) | bar: 2019-07-01 W1 to 2019-12-01 W4
2.91 pick quick success projects to tackle based on learning from engagement
2.92 determine champion to lead project
2.93 determine team from all 4 sectors
2.94 support action teams produce quick results with projects
2.95 work with working groups to oversee action teams
2.96 work with Sarah to determine measurables and indicators to report on
2.10 Presenting Community Plan | bar: 2019-10-01 W1 to 2019-12-01 W4
2.101 plan Big Gathering 2.0 for Dec-Feb area
2.102 invite top 100 back, and other engaged in process
2.103 prepare questions to spark conversation on the document thus far
2.104 craft an invitation to ask all attendees to continue their participation
2.105 revise plan and send out to top 100 + mailing list
3.0 Poverty Revealed | bar: 2019-02-01 W1 to 2019-11-01 W4
3.1 Working Group | bar: 2019-02-01 W1 to 2019-11-01 W4
3.11 re-establish working group (Steve and Sarah)
3.12 determine best framework for short timeline
3.13 determine marketing strategy to get content researchers (w/ LEAG)
3.14 Connect with Dr. Guta on process and training for data gathering
3.15 determine role of leadership (eg. Add content researchers, and work all together?)
3.2 Content Researchers | bar: 2019-03-01 W1 to 2019-11-01 W4
3.21 gather group of content researchers
3.22 discuss and confirm role and direction of project
3.23 discuss and confirm best inicators to measure
3.24 determine best methods to gather data (eg. Research, community engagement, etc.)
3.25 determine compensation package
3.26 determine cross-over with Community Plan consultations
3.27 confirm communications to update community on progress of consultations
3.3 Data Collection | bar: 2019-07-01 W1 to 2019-10-01 W4
3.31 determine necessary tools for data collections
3.32 determine training required for data collection methods
3.33 determine rules for data collection and data reporting
3.34 determine best method to centralize data for analysis and reporting
3.4 Data Analysis & Presentation | bar: 2019-07-01 W1 to 2019-12-01 W4
3.41 reivew best methods to analyze data collected
3.42 analyze data with support from Dr. Guta and Stanley
3.43 produce draft report for the community
3.44 review report with those engageed through consultations (cross-over with community plan)
3.45 produce final report (report card style) for community
3.5 Documentaries
3.51 Determine 3-4 people to display
3.52 schedule and organize documentarian
3.53 support documentarian with shooting and editing
3.54 review with people before full production
3.55 release with report
4.0 CLC Growth and Sustainability
4.1 CLC Co-Chairs
4.11 determine role responsibilities for CLC with Co-Chairs
4.12 determine plan for 1 year for CLC
4.13 determine outcomes for 1 year for CLC
4.14 support Co-Chairs present plan to CLC
4.2 CLC Growth | bar: 2019-05-01 W3 to 2019-12-01 W4
4.21 support CLC determining additions for the CLC (cross-over with community plan)
4.22 support Co-Chairs in inviting new members to sit on CLC
4.23 confirm level of diversity of CLC moving forward (esp. private sector and PWLE)
5.0 Federal Election | bar: 2019-09-01 W1 to 2019-10-01 W2
5.1 Determine Strategy | bar: 2019-09-01 W1 to 2019-09-01 W2
5.11 review federal election poverty-related candidate engagement strategies
5.12 review strategies used by other poverty roundtables
5.13 determine best strategy to engage candidates
5.2 Engage Candidates | bar: 2019-09-01 W3 to 2019-09-01 W4
5.21 connect with candidates/campaign managers to organize meeting
5.22 produce questions for candidates related to poverty (LEAG cross over?)
5.23 determine best method to record responses from candidates
5.3 Media Release | bar: 2019-10-01 W1 to 2019-10-01 W2
5.31 review strategies to use media to cover candidate conversations
5.32 determine best media strategy to increase voter turnout and media coverage

## Com Plan
Projects | 2019 Timeline
| 2019-01-01 |  |  |  | 2019-02-01 |  |  |  | 2019-03-01 |  |  |  | 2019-04-01 |  |  |  | 2019-05-01 |  |  |  | 2019-06-01 |  |  |  | 2019-07-01 |  |  |  | 2019-08-01 |  |  |  | 2019-09-01 |  |  |  | 2019-10-01 |  |  |  | 2019-11-01 |  |  |  | 2019-12-01
| W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
2.0 Community Plan
2.1 Working Group
2.2 Top 100 exercise | bar: 2019-01-01 W1 to 2019-02-01 W1
2.3 Letter of Invitation | bar: 2019-01-01 W1 to 2019-02-01 W3
2.4 Presentations | bar: 2019-01-01 W1 to 2019-03-01 W2
2.5 Agenda | bar: 2019-01-01 W1 to 2019-04-01 W2
2.6 Big Gathering | bar: 2019-01-01 W1 to 2019-05-01 W3
2.7 Support Leadership
2.8 Listening Teams | bar: 2019-04-01 W2 to 2019-12-01 W4
2.9 Quick-win Action Teams | bar: 2019-07-01 W1 to 2019-12-01 W4
2.10 Presenting Community Plan | bar: 2019-10-01 W1 to 2019-12-01 W4
2.0 Community Plan
2.1 Working Group
2.11 determine 3-4 people to sit on working group
2.12 contact and prep group members to join
2.13 send letters of participation (incl. total time per month, time outside meetings, assoc. tasks)
2.14 confirm participation, schedule meetings
2.15 draft community engagement strategy
2.2 Top 100 Exercise | bar: 2019-01-01 W1 to 2019-01-01 W4
2.21 send sector-ranked top 100 list to CLC
2.22 rank people in each sector w/ CLC
2.23 determine 1-2 people per sector as representatives to invite other top 100
2.24 determine which member of CLC to contact representatives
2.25 support CLC memebers contact and gain commitment of representatives
2.3 Letter of Invitation | bar: 2019-01-01 W1 to 2019-02-01 W3
2.31 review example letter from Iowa
2.32 determine areas needing change
2.33 retrieve community-based stats to add to letter
2.34 personalize letters for each sector with name of sector representative
2.35 review letter with working group and CLC
2.36 support CLC members sending letter through representatives (2 month before BG)
2.4 Presentations | bar: 2019-01-01 W1 to 2019-04-01 W2
2.41 review 3 types of presentations
2.42 seek example presentations from Iowa for layout, design, and information required
2.43 retrieve required stats with working group
2.44 design presentations for Big Gathering
2.45 review presentations with Paul
2.46 review presentations with working group
2.5 Agenda | bar: 2019-03-01 W2 to 2019-04-01 W2
2.5 review example agenda from Iowa
2.51 determine agenda layout and flow
2.52 create draft agenda based on Iowa's layout
2.53 review agenda with Paul and working group
2.6 Big Gathering Logistics | bar: 2019-01-01 W1 to 2019-05-01 W3
2.61 determine date and location of Big Gathering
2.62 determine location of Big Gathering
2.63 gather and train recording team
2.64 organize food, seating, and other logistics for the Big Gathering
2.65 Update website to host event page
2.66 Confirm attendance of top 100 partners
2.67 confirm attendees have correct information on Big Gathering
2.68 identify and confirm a facilitator for the event - Paul?
2.69 attend other events in CK to build momentum up to the Big Gathering
2.610 identify and confirm speakers for various parts (representatives?)
2.611 create marketing materials (eg. Sticky note wall, signs, badges, pamphlets, etc.)
2.612 develop ask (willingness to receive more communication, co-host consultations, sit on CLC, etc. )
2.7 Support CLC
2.71 work closely with CLC Co-Chairs to confirm understanding of new directions
2.72 engage CLC in activities related to the Big Gathering and Commmunity Plan
2.73 confirm all CLC attendance at Big Gathering
2.8 Listening Teams | bar: 2019-04-01 W2 to 2019-12-01 W4
2.81 seek volunteers for the listening teams
2.82 establish listening team
2.83 establish schedule (dates and locations) of community meetings, focus groups, interviews
2.84 schedule listening team to gather input and data (cross-over with Poverty Revealed)
2.85 reach out to partners to co-host engagement events
2.86 develop key questions, record answers from engagement (w/ listening team + Sarah)
2.87 develop communications to update people on what is being heard (website page?)
2.88 write a listening report
2.89 review listening report with engaged community
2.9 Quick-win Action Teams (6-8 mnts) | bar: 2019-07-01 W1 to 2019-12-01 W4
2.91 pick quick success projects to tackle based on learning from engagement
2.92 determine champion to lead project
2.93 determine team from all 4 sectors
2.94 support action teams produce quick results with projects
2.95 work with working groups to oversee action teams
2.96 work with Sarah to determine measurables and indicators to report on
2.10 Presenting Community Plan | bar: 2019-10-01 W1 to 2019-12-01 W4
2.101 plan Big Gathering 2.0 for Dec-Feb area
2.102 invite top 100 back, and other engaged in process
2.103 prepare questions to spark conversation on the document thus far
2.104 craft an invitation to ask all attendees to continue their participation
2.105 revise plan and send out to top 100 + mailing list